## IA
메뉴분류 | depth1 | depth2 | depth3 | url | views | 기획 | 디자인 | 퍼블리싱 | 프론트엔드 | 백엔드 | 전체
[6 empty] | 100% | 100% | 44.44% | 0% | 0% | 0%
대문 |  |  |  | / | /frontend/device/views/index.php | 2020-12-29 | 2020-01-06
인증 | 로그인 |  |  | /auth/signin | /frontend/device/views/auth/signin.php | 2020-12-29 | 2020-01-06 | 2021-01-11 |  |  | X
| 회원가입 | 약관동의 |  | /auth/join_agree | /frontend/device/views/auth/join_agree.php | 2020-12-29 | 2020-01-06 | 2021-01-12 |  |  | X
|  | 본인인증 |  | /auth/join_certify | /frontend/device/views/auth/join_certify.php | 2020-12-29 | 2020-01-06 | 2021-01-12 |  |  | X
|  | 정보입력 |  | /auth/join_form | /frontend/device/views/auth/join_form.php | 2020-12-29 | 2020-01-06 | 2021-01-12 |  |  | X
| 아이디찾기 | 본인인증 |  | /auth/find_id | /frontend/device/views/auth/find_id.php | 2020-12-29 | 2020-01-06 | 2021-01-13 |  |  | X
|  | 아이디 노출 |  | /auth/find_id_complete | /frontend/device/views/auth/find_id_complete.php | 2020-12-29 | 2020-01-06 | 2021-01-13 |  |  | X
| 비밀번호 찾기 | 본인인증 |  | /auth/find_password | /frontend/device/views/auth/find_password.php | 2020-12-29 | 2020-01-06 | 2021-01-13 |  |  | X
|  | 비밀번호 재설정 |  | /auth/change_password | /frontend/device/views/auth/change_password.php | 2020-12-29 | 2020-01-06 | 2021-01-13 |  |  | X
프로젝트 | 리스트(메인) |  |  | /project/list | /frontend/device/views/project/list.php | 2020-12-29 | 2020-01-06 |  |  |  | X
| 상세 |  |  | /project/detail | /frontend/device/views/project/detail.php | 2020-12-29 | 2020-01-06 |  |  |  | X
|  | 기업정보 |  | /cp/detail | /frontend/device/views/cp/detail.php | 2020-12-29 | 2020-01-06 |  |  |  | X
메뉴 | 내 정보 |  |  | /mypage/detail | /frontend/device/views/mypage/detail.php | 2020-12-29 | 2020-01-06 |  |  |  | X
|  | 내 정보 수정 |  | /mypage/update | /frontend/device/views/mypage/update.php | 2020-12-29 | 2020-01-06 |  |  |  | X
|  | 비밀번호 변경 |  | /mypage/password_change | /frontend/device/views/mypage/password_change.php | 2020-12-29 | 2020-01-06 |  |  |  | X
|  | 회원탈퇴 |  | /auth/leave | /frontend/device/views/auth/leave.php | 2020-12-29 | 2020-01-06 |  |  |  | X
| 담당자 정보 |  |  | /cp/manager_detail | /frontend/device/views/cp/manager_detail.php | 2020-12-29 | 2020-01-06 |  |  |  | X
| 서비스 이용약관 |  |  | /common/term1 | /frontend/device/views/common/term1.php | 2020-12-29 | 2020-01-06 |  |  |  | X
| 개인정보 취급방침 |  |  | /common/term2 | /frontend/device/views/common/term2.php | 2020-12-29 | 2020-01-16 |  |  |  | X